## Issues Log
22 | Task | Description | Assigned To | Time Estimate (days) | Priority | Status | Comments
1 | projectvaardigeden les 1 (1) | lees hoofdstuk 1 | Dagmar | 0.3 | 30 | ok
2 | projectvaardigeden les 1 (2) | lees hoofdstuk 2 | Dagmar | 0.3 | 30 | ok
3 | projectvaardigeden les 1 (3) | lees hoofdstuk 3 | Dagmar | 0.3 | 30 | ok
4 | OGP Les 1 | oefeningen maken | Dagmar | 0.5 | 10 | ok
5 | Wiskunde Les 1 | oefeningen maken | Dagmar | 0.3 | 10 | ok
6 | Projectvaardigheden Les 2 | oefeningen maken | Dagmar | 0.5 | 30 | ok
7 | projectvaardigeden les 2 (1) | lees hoofdstuk 14 | Dagmar | 0.3 | 30 | In progress
8 | projectvaardigeden les 2 (2) | lees hoofdstuk 15 | Dagmar | 0.3 | 30 | In progress
9 | DB les 2 |  | Dagmar | 0.5 | 10 | In progress
10 | OGP Les 2 |  | Dagmar | 0.5 | 10 | In progress
11 | Wiskunde Les 2 |  | Dagmar | 0.5 | 10 | In progress
12 | Beleids les 3 |  | Dagmar | 0.5 | 10 | In progress
13 | Projectvaardigheden Les 3 |  | Dagmar | 0.5 | 10 | In progress
14 | DB les 3 |  | Dagmar | 0.5 | 10 | In progress
15 | OGP Les 3 |  | Dagmar | 0.5 | 10 | In progress
16 | Wiskunde Les 3 |  | Dagmar | 0.5 | 10 | In progress
17 | Beleids les 4 |  | Dagmar | 0.5 | 10 | In progress
18 | Projectvaardigheden Les 4 |  | Dagmar | 0.5 | 10 | In progress
19 | DB les 4 |  | Dagmar | 0.5 | 10 | In progress
20 | OGP Les 4 |  | Dagmar | 0.5 | 10 | In progress
21 | Wiskunde Les 4 |  | Dagmar | 0.5 | 10 | In progress

## Iteration 1
| Iteration 1 | [6 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days Dagmar | Completed Task Days Developer 2 | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Comments | Days of | Today Is
| Start Date | 2022-02-14 | [6 empty] | 0 | 9.3 | 9.3 |  |  |  |  | 0 | 0 |  |  |  | 2022-02-22 | Change this with =Today()
| End Date | 2022-03-14 | [5 empty] | 2022-02-14 | 1 | 9 | 9.3 | 0 |  |  |  | 0 | 1 | 0
| # of Developers | 1 | [5 empty] | 2022-02-15 | 2 | 8.6 | 9.3 | 0 |  |  |  | 0 | 2 | 0
| Efficiency Factor | 0.335 | [5 empty] | 2022-02-16 | 3 | 8.3 | 9.3 | 0 |  |  |  | 0 | 3 | 0
| Work Days Total | 28 | [5 empty] | 2022-02-17 | 4 | 8 | 8.8 | 0.5 |  |  |  | 0.5 | 4 | 0.13
| Dev Days Total | 28 | [5 empty] | 2022-02-18 | 5 | 7.6 | 8.5 | 0.3 |  |  |  | 0.8 | 5 | 0.16
| # of Task Work Days | 9.3 | 9.3 | <= total tasks |  |  |  | 2022-02-19 | 6 | 7.3 | 8.1 | 0.4 |  |  |  | 1.2 | 6 | 0.2
| m - Ideal Task Days Left | -0.33214 | [5 empty] | 2022-02-20 | 7 | 7 | 7.9 | 0.2 |  |  |  | 1.4 | 7 | 0.2
| b - Ideal Task Days Left | 9.3 | [5 empty] | 2022-02-21 | 8 | 6.6 | 7.9 | 0 |  |  |  | 1.4 | 8 | 0.18
| m - Dev Days Used | 1 | [5 empty] | 2022-02-22 | 9 | 6.3 | 7.4 | 0.5 |  |  |  | 1.9 | 9 | 0.21
| b - Dev Days Used | 0 | [5 empty] | 2022-02-23 | 10 | 6
[8 empty] | 2022-02-24 | 11 | 5.6
Task Id | Title | Estimate | Status |  | Get Estimate | Get Title | Get Status | 2022-02-25 | 12 | 5.3
1 | projectvaardigeden les 1 (1) | 0.3 | ok |  | 0.3 | projectvaardigeden les 1 (1) | ok | 2022-02-26 | 13 | 5
2 | projectvaardigeden les 1 (2) | 0.3 | ok |  | 0.3 | projectvaardigeden les 1 (2) | ok | 2022-02-27 | 14 | 4.7
3 | projectvaardigeden les 1 (3) | 0.3 | ok |  | 0.3 | projectvaardigeden les 1 (3) | ok | 2022-02-28 | 15 | 4.3
4 | OGP Les 1 | 0.5 | ok |  | 0.5 | OGP Les 1 | ok | 2022-03-01 | 16 | 4
5 | Wiskunde Les 1 | 0.3 | ok |  | 0.3 | Wiskunde Les 1 | ok | 2022-03-02 | 17 | 3.7
6 | Projectvaardigheden Les 2 | 0.5 | ok |  | 0.5 | Projectvaardigheden Les 2 | ok | 2022-03-03 | 18 | 3.3
7 | projectvaardigeden les 2 (1) | 0.3 | In progress |  | 0.3 | projectvaardigeden les 2 (1) | In progress | 2022-03-04 | 19 | 3
8 | projectvaardigeden les 2 (2) | 0.3 | In progress |  | 0.3 | projectvaardigeden les 2 (2) | In progress | 2022-03-05 | 20 | 2.7
9 | DB les 2 | 0.5 | In progress |  | 0.5 | DB les 2 | In progress | 2022-03-06 | 21 | 2.3
10 | OGP Les 2 | 0.5 | In progress |  | 0.5 | OGP Les 2 | In progress | 2022-03-07 | 22 | 2
11 | Wiskunde Les 2 | 0.5 | In progress |  | 0.5 | Wiskunde Les 2 | In progress | 2022-03-08 | 23 | 1.7
12 | Beleids les 3 | 0.5 | In progress |  | 0.5 | Beleids les 3 | In progress | 2022-03-09 | 24 | 1.3
13 | Projectvaardigheden Les 3 | 0.5 | In progress |  | 0.5 | Projectvaardigheden Les 3 | In progress | 2022-03-10 | 25 | 1
14 | DB les 3 | 0.5 | In progress |  | 0.5 | DB les 3 | In progress | 2022-03-11 | 26 | 0.7
15 | OGP Les 3 | 0.5 | In progress |  | 0.5 | OGP Les 3 | In progress | 2022-03-12 | 27 | 0.3
16 | Wiskunde Les 3 | 0.5 | In progress |  | 0.5 | Wiskunde Les 3 | In progress | 2022-03-13 | 28 | 0
17 | Beleids les 4 | 0.5 | In progress |  | 0.5 | Beleids les 4 | In progress
18 | Projectvaardigheden Les 4 | 0.5 | In progress |  | 0.5 | Projectvaardigheden Les 4 | In progress
19 | DB les 4 | 0.5 | In progress |  | 0.5 | DB les 4 | In progress
20 | OGP Les 4 | 0.5 | In progress |  | 0.5 | OGP Les 4 | In progress
21 | Wiskunde Les 4 | 0.5 | In progress |  | 0.5 | Wiskunde Les 4 | In progress
| Testing, create svn tag, build release | 0
| Total Tasks Assigned | 9.3
| Available Time - Assigned time | 0
Formulas:
Work Date = (C2) + [Work Days, row above]